{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["新增开发项目","持续性开发项目","产品采购项目"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"新增开发项目","index":0,"n_rows":44,"n_cols":4,"rows_kept":44,"cut":false,"hidden":false,"merged":[[6,0,7,0],[9,0,10,0],[11,0,12,0],[15,0,16,0],[17,0,18,0],[20,0,21,0],[22,0,23,0],[25,0,26,0],[6,1,7,1],[9,1,10,1],[11,1,12,1],[15,1,16,1],[17,1,18,1],[20,1,21,1],[22,1,23,1],[25,1,26,1]]}
[]
["编号","新增开发项目阶段","交付物","备注"]
[1,"立项","立项报告，审批通过"]
[2,"招标","邀标文件","IT负责技术方案"]
[3,"合同","合同"]
[4,"启动会","项目说明书","项目说明书中需要包含项目计划、人员、职责等要素"]
[5,"需求管理","需求文件"]
[null,null,"业务部门确认通过"]
[6,"计划","项目计划","进行WBS分解并明确到资源的计划"]
[7,"变更管理","变更申请表"]
[null,null,"业务部门确认通过"]
[8,"概要设计","概要设计说明书"]
[null,null,"数据库设计说明书"]
[9,"详细设计","详细设计说明书"]
[10,"编码","代码"]
[11,"系统测试","测试用例"]
[null,null,"测试报告 ","测试报告中要包含测试结果及缺陷统计等信息"]
[12,"用户测试","用户宣讲资料或相关邮件（可选）"]
[null,null,"用户确认"]
[13,"上线","上线评审 "]
[14,"培训","培训资料 "]
[null,null,"客户签到表"]
[15,"项目验收","验收报告"]
[null,null,"产出物清单"]
[16,"结项","项目总结报告"]
[17,"所有阶段","周报（含风险/重大问题跟踪表）"]
[null,null,"周例会及会议纪要"]
[]
[null,null,"项目部署文档 黄勇"]
[null,null,"上线方案 黄勇"]
[null,null,"上线计划 黄勇"]
[null,null,"使用手册 张治发"]
[null,null,"概要设计说明书 王信"]
[null,null,"培训资料(PPT) 赵志强"]
[null,null,"项目总结报告 赵志强"]
[null,null,"测试报告 赵志强"]
[]
["编号","需会议评审里程碑"]
[1,"启动会"]
[2,"需求阶段"]
[3,"设计阶段"]
[4,"测试用例评审"]
[5,"上线评审"]
[6,"项目验收（可选）"]

{"sheet":"持续性开发项目","index":1,"n_rows":30,"n_cols":5,"rows_kept":30,"cut":false,"hidden":false,"merged":[[1,1,1,2],[25,1,25,2],[26,1,26,2],[27,1,27,2],[28,1,28,2],[29,1,29,2],[30,1,30,2],[5,0,6,0],[10,0,11,0],[12,0,13,0],[14,0,15,0],[16,0,17,0],[18,0,19,0],[21,0,22,0],[5,1,6,1],[10,1,11,1],[12,1,13,1],[14,1,15,1],[16,1,17,1],[18,1,19,1],[21,1,22,1],[10,2,11,2],[12,2,13,2],[14,2,15,2],[16,2,17,2],[18,2,19,2],[21,2,22,2],[5,4,6,4],[7,4,19,4]]}
[]
["编号","持续性开发项目阶段",null,"交付物","备注"]
[1,"立项",null,"立项报告（年度），审批通过"]
[2,"招标",null,"单一来源采购文件"]
[3,"合同",null,"合同"]
[4,"计划",null,"月度需求对应计划","计划制定后严格按照计划执行"]
[null,null,null,"每个需求的详细对应计划"]
[5,"需求",null," ","需求对应过程"]
[null,5.1,"需求分析","需求分析文档"]
[null,5.2,"需求分析确认","业务部门确认过"]
[null,5.3,"设计","概要\\详细设计选一"]
[null,null,null,"重大设计需要有评审记录"]
[null,5.4,"编码","代码"]
[null,null,null,"单元测试报告"]
[null,5.5,"系统测试（DAT）","测试用例"]
[null,null,null,"测试报告(含缺陷记录)"]
[null,5.6,"用户测试(UAT)","用户确认"]
[null,null,null,"UAT测试报告"]
[null,5.7,"上线","上线评审"]
[null,null,null,"发布计划"]
[6,"结项",null,"季度后评估报告，签字通过","报告内容包含工作量、验收单等"]
[7,"所有阶段",null,"周报含风险/重大问题跟踪表"]
[null,null,null,"周例会及会议纪要","外包商不驻场的情况可以采用其他方式沟通"]
[]
[]
["编号","需会议评审里程碑",null,"备注"]
[1,"需求阶段（较大需求）",null,"需求大小可根据涉及系统个数、修改周期等确定"]
[2,"设计阶段（较大需求）"]
[3,"测试用例评审（较大需求）"]
[4,"上线评审（各版本上线）"]

{"sheet":"产品采购项目","index":2,"n_rows":25,"n_cols":4,"rows_kept":25,"cut":false,"hidden":false,"merged":[[7,0,8,0],[9,0,10,0],[12,0,13,0],[14,0,15,0],[17,0,18,0],[7,1,8,1],[9,1,10,1],[12,1,13,1],[14,1,15,1],[17,1,18,1]]}
[]
["编号","产品采购项目阶段","交付物","备注"]
[1,"立项","立项报告，审批通过"]
[2,"招标","邀标文件","IT负责技术要求及评分"]
[3,"合同","合同"]
[4,"启动会","项目说明书","项目说明书中包含项目计划、人员、职责等要素"]
[5,"计划","项目计划"]
[6,"系统测试","测试用例"]
[null,null,"测试报告"]
[7,"用户测试","用户确认邮件，签字确认"]
[null,null,"用户宣讲资料或相关邮件"]
[8,"上线","上线评审（可选）"]
[9,"培训","培训资料","包含说明文档、操作手册等"]
[null,null,"客户签到表"]
[10,"项目验收","验收报告"]
[null,null,"产出物清单"]
[11,"结项","项目总结报告"]
[12,"所有阶段","周报含风险/重大问题跟踪表"]
[null,null,"周例会（可选）"]
[]
[]
["编号","需会议评审里程碑"]
[1,"启动会"]
[2,"上线评审会（可选）"]
[3,"项目验收会（可选）"]